## Sheet2
This is a sample RASCI matrix for a generic “innovation project.” We’ve color-coded things to show how the color coding works, but your coding will be different. For more details on how to use this matrix, see the usage guide below. For more resources like this, visit innovationleader.com/resources.
Legend
R | Responsible | Role responsible for execution of task
A | Accountable | Single person who is on the hook for delivery; has yes/no authority
S | Supportive | Person(s) playing a supporting role, directly assisting responsible party
C | Consulted | Person or team who may weigh in; provide input to the task
I | Informed | Person or team who should be informed of progress for that task
RASCI Matrix for Innovation Project
|  |  | Chief Innovation Officer | Chief Technology Officer | Chief Marketing Officer | Innovation Steering Committee | Innovation Manager | Product Owner | Project Manager | IT Architect | Legal/Compliance | Marketing Manager | Sales Manager | Operations Manager | Business Analyst | Lead Developer | Customer Insights/Market Research | External Consultancy | Creative Freelancers | Customers/End Users | Statisticians/Analytics | Finance Manager
|  |  | Leadership |  |  |  | Core Project Team |  |  |  | Extended Team | [6 empty] | External Resources
Innovation Strategy | Problem identification Vision and scope definition Resources identified and procured | Innovation Vision Definition | A | C | C | R | S | [10 empty] | C |  |  |  | I
|  | Scope Definition | A | C | C | R | S | [10 empty] | C |  |  |  | I
|  | Screening Criteria | A | I | I | C | R | [10 empty] | C |  |  |  | I
|  | Resource Strategy | A | C | C | R | I | I | I | I | I | I | I | I | I | I | I | I |  |  | I | I
|  | Budget Definition | A A: A; I C: C; I C: I; C R: R; R I: I |  |  |  | C
|  | Business Problem Selection/ Identification | A | C | C | R | S | I | I | I | I | I | I | I | I | I | I | C |  |  | S | I
Ideation | Initial solution set identification Business requirements not known Idea sources could come from anywhere | Background Research | I | I | I | I | A | C | I | C | C | C | C |  |  |  | R | C |  |  | S
|  | Customer Immersion | I | I | I | I | A | S | I | I | I | S | I | I | I | I | R | S |  | C | I
|  | Customer Empathy & Journey Maps | I | I | I | I | A | I | I | I | I | S | I | I | I | I | R | S |  |  | S
|  | Existing Idea Gathering | A A: A; S I: R; R R: S
|  | New Idea Generation | C | C | C | C | A | C | C | C | C | C | C | C | C | C | S | R |  | S | C | C
|  | Idea Scoring & Screening | I | I | I | I | A | R | C | C | C | C | C | C | C | C | S | C |  | C | C | C
|  | Conceptualization | A A A: A; R C R: R; R C C: C; S S S: C; S R C: C | S
|  | Consumer Concept Vetting | I | I | I | I | A | S | I | I | I | S | I | I | I | I | R | S |  | C | I
|  | Business Concept Vetting |  |  |  |  | A | R |  | C | C | C | C | C | C | C |  | S |  |  | C | C
|  | Concept Scoring & Screening | C | C | C | C | A | R | C | C | C | C | C | C | C | C | S | C
|  | Concept Approval | A | C | C | C | R | S | I | I | I | I | I | I | I | I | I | S |  |  | I | I
Design | Pre-alpha development phase Business requirements identification Technical requirements not known | Design Sessions | I | I | I | I | A | S | C | C | C | C | C | C | C | C | C | R | S | C
|  | Concept Prototype Co-Creation | A R A: A; R S S: S; C I C: S; C I C: C; C I C: C; C S R: R; C S S: S
|  | Concept Prototype Feasilbility Assessments |  |  |  |  | A | R | C | C | C | C | C | C | S | C | C | C |  | C | C | C
|  | Initial Business Requirement Development |  |  |  |  | A: C; R: A; C: S; C: C; C: C; C: C; S: R
|  | Design Approval/ Alpha Pitch | A | C | C | C | S | R | C | I | I | I | I | I | S | I | I | S |  |  | I | I
Prototyping | a/k/a Alpha testing phase Product specs developed Target architecture/manufacturing process identified | Product Spec Development | C S: C; A R: A; S C: R; C I: S; C I: C; R S: S; R I: S
|  | Prototype Develpoment | I | I | I | I | C | A | R | S | I | I | I | C | S | S | I | C
|  | Business Requirement Iteration | C C: C; A A: A; R R: S; S S: C; S I: C; S I: C; S S: R
|  | Technical Development Asssessment | I: C; C C: I; A A: I; R R: R; S S: A; C C: C; S S: S; S S: S
|  | Prototype Approval/ Beta Pitch | A | C | C | C | S | R | S | S | C | I | I | I | S | I | I | S
Build and Launch | a/k/a Beta testing phase Minimum viable product: limited feature set Solution architecture integration/manufacturing development/deployment plan | Business Requirement Iteration | S: C; R: A; S: S; S: C; I: C; I: C; S: R
|  | Feature Set Development & Prioritization | I | I | I | I | S | A | R | C | C | C | C | C | C | C | C | S |  | C | C
|  | Backlog Creation |  |  |  |  | S | R | A | S | I | I | I | I | C | C | I | C
|  | Technical Requirement Development |  | C |  |  | A A R: C; S R A: A; C C S: R; R C C: S; R C C: S
|  | Development | I | I |  |  | I | C | A | S | C | S | I | I | S | R | I |  | S
|  | Integration & Testing | I | I |  |  | I | C | A | R |  |  |  | C | S | S
|  | Beta Launch | I | I | I | I | I | A | R | S | C | I | I | C | C | C | I |  |  |  | I
|  | Monitoring, Defects & Analytics | I | I | I | I | I | A | S | S | I | S | I | I | S | I | I |  |  |  | R
|  | Production Pitch & Approval | A | C | C | C | S | R | S | S | C | C | I | I | I | I | I | S |  |  |  | I
Production and Post-Production | Production phase Resources may shift substantially Feature set sufficiently complete Versioning/enhancement plans developed Product fully supported, deployed, and integrated | Resource/Product Owner Transition | C | C | A | C | I | R | I | I | I | I | I | I | I | I | I |  |  |  | I | I
|  | Feature Set Refinement | I | I | I | I | I | A | R | C | C | C | C | C | C | C | C | S |  | C | C
|  | Backlog Re-prioritization |  |  |  |  | C | R | A | S | I | I | I | I | C | C | I | C
|  | Versioning Strategy |  |  |  |  | C | R | A | S | I | I | I | I | C | C | I | C
|  | Production Release | I | I | I | I | I | A | R | S | C | I | I | C | C | C | I |  |  |  | I
|  | Monitoring, Defects & Analytics | I | I | I | I |  | A | S | S | I | S | I | I | S | I | I |  |  |  | R
|  | New Version Releases | I | I | I | I | I | A | R | S | C | I | I | C | C | C | I |  |  |  | I
USAGE GUIDE: To adapt this RASCI matrix for use in your organization, follow these steps... 1. Survey your organization for the complete set of stakeholders in a given innovation project 2. Map out all of the project stages and tasks associated with innovation in your organization 3. On the vertical axis of the matrix, list all of the innovation tasks/stages 4. On the the horizontal axis of the matrix, list the set of roles required to complete the work 5. Then, for each task populate the matrix with the letters R, A, S, C, and I by determining: • Who is the single ACCOUNTABLE resource (“A”) who has yes/no authority and is on the hook for the task? • Who is RESPONSIBLE for executing the task (“R”)? Typically, there is only one responsible resource, and this may be the same as the accountable resource • Who will SUPPORT (“S”) the responsible resource in the execution of the task? There may be several support resources. • Who else may be CONSULTED (“C”) on a various task? These are resources who may weigh in, or provide input or guidance on a task. • Who should be INFORMED (“I”) of the progress or output of that task? 6. Finally, review the matrix with all resources. Some questions to consider at this step include: • Does everyone buy-in to and agree with their tasks? • Does each resource truly need to be informed/consulted at each step? How can this be minimized as to not impede rapid progress? • What exceptions might arise? • Are any of the resources overburdened or underutilized? • Is there opportunity to stretch someone to be responsible for a task they typically wouldn’t perform?
Role
Project Stage and Deliverable